## Front Sheet
Company | [Company Name]
Document | Risk Register
Classification | Confidential
Version Control
Version | Document Changes | Last Modified By | Date
0.1

## Dashboard
[Company] : Risk Register Dashboard
Classification: Confidential
DATE:
RISK STATUS |  | RISK TREATMENT |  | RISKS WHEN FIRST IDENTIFIED |  | RESIDUAL RISK
Number of Risks |  | Risk Treatment |  | Risk Levels |  | Risk Levels
Open Risks | 6 | Risk Avoidance | 1 | Minor | 8 | Minor | 10
Closed Risks | 1 | Risk Reduction | 0 | Moderate | 3 | Moderate | 3
Total Risks | 7 | Risk Acceptance | 6 | Major | 1 | Major | 0
|  | Risk Transfer | 0 | Critical | 1 | Critical | 0

## Risk Register
[Company] : Risk Register
Classification: Confidential
[11 empty] | Original Risk | [10 empty] | Residual Risk
Ref | External Ref | Risk Description | Date Open | Date Closed | Asset | Asset Owner | Threat | Vulnerability | Outcome | CIA | Existing Control | Impact | Likelihood | Risk Score | Risk Rating | Risk Owner | Risk Treatment | Treatment Plan | Treatment Owner | Treatment Date | Open / Closed | New Control | Impact | Likelihood | Risk Score | Risk Rating | Last Review Date | Next Review Date | Relevant ISO27001 Annex A Control
1 | Risk Review Meeting <date> | Staff are unaware of what is required of them |  |  | Information Security Policies |  | No policy or policy not fit for purpose | Policy doesn’t exist or is missing or is not fit for purpose | Lack of policy and training leads to breaches in information security due to lack of direction on what is expected | CIA | A full set of information security policies mapped to the relevant standards exists and is communicated. A training schedule is in place and staff are trainined | 1 | 1 | 1 | Minor |  | Risk Acceptance | Monitor for effectiveness |  |  | Closed | The current control is effective | 1 | 1 | 1 | Minor
2 | Risk Review Meeting <date> | Internally there are no resources trained or experienced in the delivery of ISO 27001 |  |  | Information Security Policies |  | No trained resources | Staff knowledge and experience does not meet the needs of ISO 27001 | Lack of trained resources leads to breaches in information security | CIA | None in place | 5 | 5 | 25 | Critical |  | Risk Avoidance | Hire qualified extenral resource |  |  | Open | High Table have been engaged and Stuart Barker has joined as information security manager to support the project. | 5 | 1 | 5 | Moderate
3 | Risk Review Meeting <date> | Risk that Company endpoints are compromised and this lead to a breach of confidentiality, integrity or availablity of client systems |  |  | Client Systems |  | Information is compromised for CIA due to ineffective policies or technical controls | Policy doesn’t exist or is missing or is not fit for purpose. Technical controls are not operating effectively | Security breach in breach of contract / law that leads to loss of client or legal consequences. | CIA | A full set of policies is in place to address information security and they are approved, communicated and agreed. End point device contols is in place for anti malware, encryption and patching. | 5 | 2 | 10 | Major |  | Risk Acceptance | Whilst the control is currently effective it relies on manual process and intervention and the company will move to <InTune> for Endpoint managmeent before the end of <date>. |  |  | Open | <InTune> in place and operating | 5 | 1 | 5 | Moderate
4 | Risk Review Meeting <date> | Compromise at suppliers leads to to a breach of confidentiality, integrity or availablity of client systems |  |  | Client Systems |  | Information is compromised for CIA due to ineffective policies or technical controls at suppliers | Supplier contracts not existing and no evidence of certifications | Security breach in breach of contract / law that leads to loss of client or legal consequences. | CIA | Effective supplier management is in place with assurance for inscope suppliers and ISO 27001 certificates checked. | 5 | 1 | 5 | Moderate |  | Risk Acceptance | The current control is effective |  |  | Open | The current control is effective | 2 | 1 | 2 | Minor
6 | Risk Review Meeting <date> | Loss of Microsoft 365 prevents clients from contacting us via email or teams |  |  | Client Systems |  | In ability to communicate | The potentail for lack of availabilty at supplier | Loss of client confidence, impact to SLA | A | Supplier contract in place with Microsoft and reliace place on their security certifications such as ISO 27001 | 2 | 1 | 2 | Minor |  | Risk Acceptance | The current control is effective |  |  | Open | The current control is effective | 5 | 1 | 5 | Moderate
7 | Risk Review Meeting <date> | System is unavailable to clients |  |  | Client Systems |  | In ability to operate commericailly | No continuity in place for client facing systems | Security breach in breach of contract / law that leads to loss of client or legal consequences. | A | Business Continuity Plans are in place and tested at least annually | 5 | 1 | 5 | Moderate |  | Risk Acceptance | The current control is effective |  |  | Open | The current control is effective | 1 | 1 | 1 | Minor
8 | Risk Review Meeting <date> | Data Breach |  |  | Company owned systems / Client Data / Customer Data / Employee Data |  | Data is compromised for CIA | Staff knowledge on what is required, technical controls inadequate | Security breach in breach of contract / law that leads to loss of client or legal consequences. | CIA | Policies in place and communicated and accepted, training in place and evidenced, end point management in place, patching in place, logging and monitoring in place, incident management in place. | 5 | 1 | 5 | Moderate |  | Risk Acceptance | The current control is effective |  |  | Open | The current control is effective | 2 | 1 | 2 | Minor
9 | [13 empty] | 0 | Minor | [9 empty] | 0 | Minor
10 | [13 empty] | 0 | Minor | [7 empty] | 5 |  | 0 | Minor
11 | [13 empty] | 0 | Minor | [9 empty] | 0 | Minor
12 | [13 empty] | 0 | Minor | [9 empty] | 0 | Minor
13 | [13 empty] | 0 | Minor | [9 empty] | 0 | Minor
14 | [13 empty] | 0 | Minor | [9 empty] | 0 | Minor
[12 empty] | 1 | 1
[14 empty] | Dashboard Summary | [10 empty] | Dashboard Summary
[14 empty] | Number Minor | 8 | Risk Avoidance | 1 |  |  | Open Risks | 6 |  |  |  | Number Minor | 10
[14 empty] | Number Moderate | 3 | Risk Reduction | 0 |  |  | Closed Risks | 1 |  |  |  | Number Moderate | 3
[14 empty] | Number Major | 1 | Risk Acceptance | 6 |  |  | Total Risks | 7 |  |  |  | Number Major | 0
[14 empty] | Number Critical | 1 | Risk Transfer | 0 | [7 empty] | Number Critical | 0

## Scoring
Risk Scoring
| Likelihood |  |  |  | Impact
| Likelihood | Grading | Description |  | Impact | Grading | Description
| Highly Probable | 5 | Likely to happen within the next month |  | Very High | 5 | Legal or regulatory compliance issue or breach System downtime in breach of agreed SLA’s, leading to contract loss. Impact on health or safety or individuals.
| Probable | 4 | Likely to happen within the next 6 months | x | High | 4 | Exposure of sensitive information to a non-authorised third party, system downtime, data corruption, impacting upon ability to deliver service (breaching agreed SLA’s)
| Possible | 3 | Likely to happen once within the next 2 years |  | Medium | 3 | Internal exposure of sensitive information beyond authorised individuals, system downtime, or data corruption with minor disruption to customer service (within agreed SLA’s)
| Unlikely | 2 | Likely to happen once within the next 5 years |  | Low | 2 | Detected security incident with no direct impact on operations or exposure to information
| Rare | 1 | Highly unlikely to occur - Less than once in the next 10 years |  | Very Low | 1 | No perceived impact
Risk Classification and Risk Treatment Default
| Risk Classification | Grading | Description
| Critical | 16 >= | Reduce risk
CEO authority required to accept risk at this level.
| Major | 10 - 15 | Reduce risk
= |  |  | Management Review Team authority required to accept risk at this level.
| Moderate | 5 - 9 | Reduce risk
Management Review Team authority required to accept risk at this level.
| Minor | 1 - 4 | Accept Risk

## ISO27001 Mapping
Areas of the ISO 27001 Standard Addressed
Risk Regsiter Relevant ISO 27001 Controls Mapping
ISO27001:2022 | ISO27002:2022 | ISO27001:2013/2017 | ISO27002:2013/2017
ISO27001:2022 Clause 5.2 Policy | ISO27002:2022 5.19 Information security in supplier relationships | ISO27001:2013/2017 Clause 5.2 Policy | ISO27002:2013/2017 15.1 Information security in supplier relationships
ISO27001:2022 Clause 6 Planning | ISO27002:2022 5.24 Information security incident management planning and preparation | ISO27001:2013/2017 Clause 6 Planning | ISO27002:2013/2017 16.1 Management of information security incidents and improvements
ISO27001:2022 Clause 6.1 Adctions to address risks and opportunities | ISO27002:2022 5.25 Assessment and decision on information security events | ISO27001:2013/2017 Clause 6.1 Adctions to address risks and opportunities
ISO27001:2022 Clause 6.1.1 General Adctions to address risks and opportunities | ISO27002:2022 5.26 Response to information security incidents | ISO27001:2013/2017 Clause 6.1.1 General Adctions to address risks and opportunities
ISO27001:2022 Clause 6.1.2 Information Security Risk Assessment | ISO27002:2022 5.27 Learning from information security incidents | ISO27001:2013/2017 Clause 6.1.2 Information Security Risk Assessment
ISO27001:2022 Clause 6.1.3 Information Security Risk Treatment |  | ISO27001:2013/2017 Clause 6.1.3 Information Security Risk Treatment
ISO27001:2022 Clause 6.2 Iinformation Security Objectives and Planning to achieve them |  | ISO27001:2013/2017 Clause 6.2 Iinformation Security Objectives and Planning to achieve them
ISO27001:2022 Clause 8.2 Information Security Risk Assessment |  | ISO27001:2013/2017 Clause 8.2 Information Security Risk Assessment
ISO27001:2022 Clause 8.3 Information Security Risk Treatment |  | ISO27001:2013/2017 Clause 8.3 Information Security Risk Treatment